## Cost Model
Crossed Arrows Lot 3 — Build-Out Cost Model
Planning-grade estimate (±25%), 2026 Teton Valley dollars. Edit the blue cells to re-run.
Legend: blue = input you can edit · yellow = key assumption · green = linked cell · black = calculated
GLOBAL ASSUMPTIONS
Soft costs (design, engineering, permits, impact fees) | 13% |  |  | % of hard cost, each phase
Contingency | 10% |  |  | % of hard cost; 5–10%+ recommended
Land cost (separate from build-out) |  |  | 500000 | ~24-ac comp bracket; ask seller for real number
SHARED SITE INFRASTRUCTURE (build once, in Phase 1, sized for full build-out)
Well — drill + pump + pressure tank + permit |  |  | 15000 | Shallow locally (~60–105 ft); serves both structures
Septic — engineered/mound, sized for full build-out |  |  | 32000 | Drainfield sized for total bedrooms now (EIPH)
Electric — Fall River line ext + service (oversized) |  |  | 22000 | Panel/service sized for house + ADU
Driveway (gravel) + culvert + approach permit |  |  | 18000 | Built to final layout
Site prep — clear / grade whole site once |  |  | 18000 | Grade for both structures + house pad up front
Phase-2 readiness — stub utilities to house pad |  |  | 12000 | Water/power/conduit stubs so Phase 2 won't tear up finished ground
Shared site subtotal
PHASE 1 — BUNKHOUSE ADU + GARAGE
Item | Size (sf) | $/sf | Amount | Notes
ADU / bunkhouse (2-bed) | 1500 | 600 |  | 1,500 sf = max ADU cap; $500–700/sf small custom
3-car garage / shop | 800 | 110 |  | ~24x34; 2-car (~576 sf) saves ~$25k
Geothermal — ADU (~3 ton) |  |  | 30000 | Vertical loop; no federal credit (expired)
Solar 7–9 kW + 1 battery |  |  | 40000 | ~$3/W + ~$13k battery
Buildings + systems subtotal
Shared site (from above)
Phase 1 hard cost
Soft costs
Contingency
PHASE 1 ALL-IN
PHASE 2 — MAIN HOUSE (single story, planned from the start)
Item | Size (sf) | $/sf | Amount | Notes
Main house | 3500 | 600 |  | 3,500 sf single-story; $500–750/sf (finish is the big dial)
Geothermal — main (~5 ton) |  |  | 55000 | Cold-climate load at ~6,200 ft
Solar expansion + 2nd battery |  |  | 35000 | Inverter/panel pre-sized in Phase 1
Phase 2 hard cost
Soft costs
Contingency
PHASE 2 ALL-IN
ALL-IN SUMMARY
Phase 1 (bunkhouse + garage + full site)
Phase 2 (main house)
BUILD-OUT TOTAL
Land (if purchased — separate)
TOTAL INCLUDING LAND
Planning-grade (±25%), not a bid. Excludes furnishings, landscaping beyond defensible space, snow-melt, financing carry. Finish level is the master dial (~$1M swing across $500–750/sf). Federal 30% energy credit expired 2025-12-31. Shared site is built once in Phase 1 and sized for the whole property so Phase 2 adds only the house. Verify $/sf with a local GC and septic type with EIPH test holes.
Note on C6: Soft costs 12–15% locally; architecture alone 8–12% of construction.
Note on D21: Small structures cost MORE per sf. Teton Valley small-custom $500–700/sf.
Note on D34: $500 simple/efficient to $750 sleek w/ big glass. Single-story adds cost per sf.